## Sheet1
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | No | No | High | In Progress | 24 | No
Task 1 | Yes | Yes | Medium | Complete | 8 | Yes
Task 2 | Yes | Yes | Medium | Complete | 16 | Yes
Task 3 | Yes | Yes | Medium | Complete | 0 | Yes
Sprint 2 | Yes | Yes | Medium | In Progress | 96 | Yes
Task 4 | Yes | Yes | Low | Complete | 32 | Yes
Task 5 | Yes | Yes | Low | Complete | 48 | Yes
Task 6 | No | No | Medium | Not Started | 16 | No
Sprint 3 | Yes | No | Medium | In Progress | 32 | No
Task 7 | Yes | No | Low | In Progress | 8 | No
Task 8 | No | Yes | Medium | In Progress | 8 | No
Task 9 | Yes | No | Medium | In Progress | 16 | No
Sprint 4 | Yes | Yes | Medium | In Progress | 64 | Yes
Task 10 | Yes | No | Low | In Progress | 32 | No
Task 11 | Yes | Yes | Low | Complete | 32 | Yes
Task 12 | Yes | Yes | Medium | Complete | 0 | Yes
Sprint 5 | No | No | Low | Not Started | 64 | No
Task 13 | No | No | Low | Not Started | 48 | No
Task 14 | No | No | Low | Not Started | 8 | No
Task 15 | No | No | Low | Not Started | 8 | No

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started